## Sign-off
The American Club — Website UAT Sign-off
Environment | UAT — https://uat.amclub.org.sg (admin: /admin)
Build / commit | ______________________ (git short SHA on uat)
Tester name | ______________________
Role | ______________________
Test start date | ______________________
Sign-off date | ______________________
Overall result | PASS / PASS-WITH-NOTES / FAIL
Approved by (name) | ______________________
Signature | ______________________
How to use
• Work through each tab. Set Status to Pass / Fail / Blocked / N/A / Not tested (dropdown).
• Put the reproduction + screenshot link in Notes for any Fail/Blocked.
• 'Just test 1 representative entry' per collection is sufficient for field checks.
• Test on UAT only. Do NOT sign off against dev.
Status legend
Pass — works as expected. Fail — defect (log in Notes). Blocked — cannot test (dependency).
N/A — not applicable. Not tested — pending.

## 1. Content Editability
1. Content Editability
One row per content type (17 collections + 22 singles = 39). For collections, testing one representative entry is enough.
# | Type | CMS name (Content Manager) | Public page to verify | Fields | Test steps | Expected | Status | Tester | Date | Notes
1 | Collection | About: Committee Members | /about (General Committee section) | 7 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
2 | Collection | Dining: Promotions | /dining/dining-promotion | 13 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
3 | Collection | Dining: Restaurants | /dining/grillhouse (any restaurant) | 25 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
4 | Collection | Event Spaces: Venues | /event-spaces/the-gallbrainth-ballroom (any venue) | 22 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
5 | Collection | FAQ: Categories | /faq | 5 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
6 | Collection | FAQ: Items | /faq | 6 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
7 | Collection | Fitness: Aquatics Coaches | /fitness/aquatics (team grid) + /coaches/aquatics/<slug> | 15 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
8 | Collection | Fitness: Facilities | /fitness/tennis (any facility) | 27 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
9 | Collection | Fitness: Gym Trainers | /fitness/gym (team grid) | 15 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
10 | Collection | Fitness: Pilates Instructors | /fitness/pilates (team grid) | 15 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
11 | Collection | Fitness: Tennis Coaches | /fitness/tennis (team grid) | 15 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
12 | Collection | Gallery: Albums | /home-sub/gallery | 8 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
13 | Collection | Home: Testimonials | /home + detail pages (member quotes) | 9 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
14 | Collection | Kids: Experiences | /kids/camps (any experience) | 26 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
15 | Collection | News: Articles | /home-sub/news + /home-sub/club-news/<slug> | 9 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
16 | Collection | What's On: Categories | /whats-on (filter chips) | 4 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
17 | Collection | What's On: Events | /whats-on + /whats-on/<slug> | 17 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
18 | Single | About: Advertise With Us Page | /home-sub/advertise-with-us | 18 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
19 | Single | About: Page | /about | 14 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
20 | Single | Contact: Page | /home-sub/contact-us | 10 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
21 | Single | Dining: Page | /dining | 6 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
22 | Single | Dining: Promotions Page | /dining/dining-promotion | 7 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
23 | Single | Event Spaces: Page | /event-spaces | 7 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
24 | Single | FAQ: Page | /faq | 5 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
25 | Single | Fitness: Page | /fitness | 13 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
26 | Single | Gallery: Page | /home-sub/gallery | 5 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
27 | Single | Global: Footer | every page (footer) | 8 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
28 | Single | Global: Header | every page (top nav) | 3 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
29 | Single | Global: Site Configuration | Google Tag / analytics (see GA sheet) — no visible page | 4 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
30 | Single | Home: Page | /home | 9 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
31 | Single | Kids: Page | /kids | 11 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
32 | Single | Membership: Joining Fees Page | /membership/joining-fees | 20 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
33 | Single | Membership: Niche Group Page | /membership/niche-group-membership | 18 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
34 | Single | Membership: Page | /membership | 13 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
35 | Single | Membership: Reciprocal Clubs Page | /membership/reciprocal-clubs | 26 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
36 | Single | Membership: Referral Page | /membership/referal | 10 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
37 | Single | Membership: Start Application Page | /membership/start-application | 18 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
38 | Single | News: Page | /home-sub/news | 5 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.
39 | Single | What's On: Page | /whats-on | 5 | Content Manager → open a representative entry → edit every field → Save → Publish → open the public page and hard-refresh. | Every field is editable; Save + Publish succeed; the change shows on the public page.

## 2. Responsive
2. Responsive
Check at the 4 project breakpoints: no horizontal overflow; images/text scale; nav collapses to hamburger on mobile and the menu works; CTAs are tappable; hero/cards reflow correctly. Status per size.
# | Page | URL | Desktop XL ≥1440 | Desktop 1200–1439 | Tablet 768–1199 | Mobile <768 | Notes
1 | Home | /home
2 | About | /about
3 | Dining (landing) | /dining
4 | Dining detail | /dining/grillhouse
5 | Dining promotions | /dining/dining-promotion
6 | Fitness (landing) | /fitness
7 | Fitness detail | /fitness/tennis
8 | Kids (landing) | /kids
9 | Kids detail | /kids/camps
10 | Event Spaces (landing) | /event-spaces
11 | Event Space detail | /event-spaces/the-gallbrainth-ballroom
12 | Membership (landing) | /membership
13 | Membership sub (joining fees) | /membership/joining-fees
14 | What's On (landing) | /whats-on
15 | Event detail | /whats-on/<any-event>
16 | News | /home-sub/news
17 | News article | /home-sub/club-news/<any>
18 | Gallery | /home-sub/gallery
19 | Contact | /home-sub/contact-us
20 | FAQ | /faq

## 3. Google Analytics
3. Google Analytics
Site Configuration → Google Tag ID accepts gtag (G-/GT-/AW-) and GTM- (auto-detected). Verify tracking.
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Set Google Tag ID | Admin → Global: Site Configuration → Google Tag ID → enter the real ID (G-/GT-/AW- or GTM-) → Save + Publish. | Field saves; value persists on reload.
2 | Tag script loads | Open the public site → DevTools → Network → reload. | gtag/js (for G-/GT-/AW-) or gtm.js (for GTM-) request is made with the configured ID.
3 | Realtime hit registered | In GA4/GTM realtime, browse the site. | Your session/page_view appears in realtime.
4 | SPA page_view on navigation | Navigate between pages without full reload. | A page_view (gtag) / dataLayer page_view (GTM) fires on each route change.
5 | Disable analytics | Clear the Google Tag ID → Save + Publish → reload site. | No analytics script loads; no tracking.

## 4. SSO & User Mgmt
4. SSO & User Mgmt
Microsoft Entra SSO + password login + role separation. Done in /admin.
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Login via Microsoft SSO | /admin → 'Continue with Microsoft' → sign in with a Club account. | Logs in to the admin; lands on dashboard.
2 | Login via email + password | /admin → enter email + password → Login. | Logs in successfully.
3 | Forgot password | /admin → 'Forgot your password?' → follow email. | Reset email arrives; new password works.
4 | Invite new user | Settings → Users → Invite new user → assign role → send. | Invite created (Inactive); registration link works.
5 | Editor role restrictions | Log in as an Editor. | Can create/edit/publish content; CANNOT see Content-Type Builder / change Settings/users.
6 | Super Admin access | Log in as Super Admin. | Full access to Settings, Users, API Tokens, etc.
7 | Deactivate / remove user | Settings → Users → deactivate or delete a test user. | That user can no longer log in.
8 | SSO whitelist (if enabled) | Confirm only allowed domains/emails can SSO in. | Non-whitelisted accounts are rejected; no lock-out of admins.

## 5. Media Upload
5. Media Upload
Media Library upload + assignment + serving. Azure Blob via the folder-aware provider.
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Upload an image | Media Library → Add new assets → upload a JPG/PNG. | Uploads; thumbnail renders in the Media Library.
2 | Upload a PDF / document | Media Library → upload a PDF/doc. | Uploads and is listed.
3 | Assign image to an entry | Open an entry → image field → pick the upload → Save + Publish. | Image shows on the public page.
4 | Assign PDF to a CTA / download | Set a CTA/download href to the uploaded /uploads/...pdf → publish. | Link opens the PDF (new tab) on the public page.
5 | Replace an asset | Media Library → open asset → replace file. | New file shows everywhere it is used.
6 | Admin thumbnails (CORS) | Browse the Media Library grid. | Thumbnails load (no broken images / CORS errors).
7 | Folder organisation | Check seeded uploads sit under their folders (e.g. fitness/, dining/). | Assets are organised, not all flat under 'API Uploads'.
8 | Delete an asset | Delete a test asset. | Removed from library; references handled.
9 | File naming guidance | Upload uses lowercase-with-hyphens names. | Names follow the convention (no spaces/caps).

## 6. Chatbot (ElevenLabs)
6. Chatbot (ElevenLabs)
Publish-time KB sync + answer accuracy. Tone/manner is optional (fine-tuning).
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | KB sync on publish | Publish an allow-listed entry (e.g. an Event) with distinctive text. | Entry is upserted to the ElevenLabs KB (doc prefixed 'am-club:').
2 | Answer accuracy | Open the on-site chatbot → ask about that content. | Bot answers correctly using the published info.
3 | Expired content removed | Let an event pass its date (or set expiredAt) → wait for hourly sweep. | Bot no longer cites the expired event.
4 | Manual re-sync | On a published entry use 'Sync to ElevenLabs'. | Forces an immediate KB upsert; reflected in answers.
5 | Widget loads | Public site → chatbot widget appears and opens. | Agent responds to a simple greeting.
6 | Tone & manner (optional) | Ask a few brand questions. | Replies match the Club's voice (optional — fine-tuning).

## 7. Workflow & Rendering
7. Workflow & Rendering
Draft/publish lifecycle, clone, expiry, markdown, and CTA variants.
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Save draft is private | Edit an entry → Save (not Publish). | Change is NOT visible on the public site.
2 | Publish goes live | Publish the entry. | Change appears on the public page after refresh.
3 | Modified state | Edit a published entry → Save (don't publish). | Public still shows the OLD version until you publish.
4 | Unpublish | Entry → ⋯ → Unpublish. | Entry disappears from the public site.
5 | Clone entry | Open a collection entry → Clone entry. | Creates a draft copy with '(copy)' title and '-copy' slug.
6 | Event/promo auto-expiry | Confirm a past-dated event/promo. | Hidden from listings (still reachable by direct link).
7 | Markdown formatting | In a richtext field use headings/bold/lists. | Renders correctly on the page.
8 | Markdown link | Add [text](https://example.com) and [text](/page). | External opens new tab; internal navigates in-app.
9 | Markdown PDF link | Add [Download](/uploads/.../file.pdf). | Opens the PDF in a NEW TAB (not blank/SPA-intercepted).
10 | CTA variant | Set a CTA Variant = secondary / accent / outline / text. | Button style changes accordingly (primary/blank = white pill).
11 | CTA icon & bordered | Set a CTA icon + bordered flag. | Trailing icon + border render as chosen.

## 8. Navigation & SEO
8. Navigation & SEO
Header/footer/breadcrumbs and per-page SEO. (Forms are out of scope.)
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Header nav (desktop) | Click every top-nav item + dropdown. | All navigate to the correct page.
2 | Mobile hamburger menu | On mobile, open the menu. | Opens; all links work; closes correctly.
3 | Footer links | Click footer columns, contact details, social icons. | All resolve to correct pages/targets.
4 | Breadcrumbs | On a detail page, use the breadcrumb / 'Back to ...'. | Correct labels; link to the parent section.
5 | Logo → home | Click the header logo. | Returns to the home page.
6 | Page <title> | Check the browser tab title on several pages. | Each page has a correct, distinct title (from CMS SEO).
7 | Meta description | View source / DevTools on key pages. | meta description present and page-appropriate.
8 | OG / social preview | Paste a page URL into a link-preview tool. | Title/description/image preview render.
9 | Favicon | Check the browser tab icon. | Club favicon shows.
10 | 404 / unknown route | Visit a non-existent URL. | Graceful not-found / redirect, not a crash.

## 9. Cross-browser & Perf
9. Cross-browser & Perf
Render parity across browsers + basic performance. (Accessibility deferred.)
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Chrome (desktop) | Load key pages in Chrome. | Renders correctly; no console errors.
2 | Safari (desktop) | Load key pages in Safari. | Renders correctly.
3 | Edge (desktop) | Load key pages in Edge. | Renders correctly.
4 | Mobile Safari (iOS) | Load on an iPhone. | Renders + interactions work.
5 | Mobile Chrome (Android) | Load on Android. | Renders + interactions work.
6 | Lighthouse performance | Run Lighthouse on Home + a detail page. | Performance score within the agreed target.
7 | Load time / LCP | Observe first load. | Largest content paints quickly; no long blank screen.
8 | No console errors | Browse with DevTools console open. | No uncaught errors / failed requests.

## 10. Infra & Security
10. Infra & Security
Domain/TLS, access control, environment correctness, backups.
# | Test Case | Steps / How to test | Expected Result | Status | Tester | Date | Notes
1 | Custom domain + HTTPS | Visit the UAT URL. | Loads over HTTPS with a valid cert (Cloudflare → Azure managed cert).
2 | HTTP → HTTPS | Visit http:// of the host. | Redirects to https://.
3 | Admin requires login | Visit /admin while logged out. | Redirected to login; no content exposed.
4 | Role separation | As Editor, attempt Settings/Content-Type Builder. | Access denied / hidden.
5 | No secrets exposed | Check page source / network for tokens. | No API tokens or secrets in client payloads.
6 | Environment correctness | Confirm UAT shows UAT content. | No dev/localhost URLs or wrong-env content leaking.
7 | Media origin / CORS | Inspect image/PDF URLs on the site. | Served from the site origin (/uploads); no CORS errors.
8 | Backup / restore ready | Confirm DB backup (PITR) + a manual dump exist. | Recovery path verified before go-live.
9 | Deploy pipeline | Confirm a content/code change deploys to UAT. | Push → CI → deploy works; revision healthy.